## Instructions
INDUSTRY ACADEMIA COMMUNITY
DOMAIN NAME: | JAVA
INTERN NAME: | GUGULOTH RAJKUMAR
DOCUMENT NAME: | TEST PLAN
CREATED ON: | 2025-04-19
Purpose of Document
A Test Plan is a detailed document that describes the test strategy, objectives, schedule, estimation, deliverables, and resources required to perform testing for a software product.
Test Plan helps us determine the effort needed to validate the quality of the application under test.
The test plan serves as a blueprint to conduct software testing activities as a defined process, which is minutely monitored and controlled by the test manager
INSTRUCTIONS:
1. Text in Italics are instructions for completing the document
2. Text in orange is just for reference and should be deleted before submitting the document
3. Comments are added to some of the cells, please read the comments to better understand the terms
4. All fields must be duly filled

## TEST PLAN
TEST PLAN
PROJECT NAME | IAC 'Community Ambassador Onboarding Process'
PROJECT ID | IP-6444
INTERN NAME | Guguloth Rajkumar
PROJECT MANAGER | Harshada Topale
INTRODUCTION
(Brief introduction of the test strategies, process, workflow and methodologies used for the project)
This project follows a Unit and manual testing strategy combined with functional and integration testing approaches. The testing process ensures the application meets specified requirements, functions correctly, and integrates properly across modules. The testing methodology is influenced by the Waterfall model due to the sequential phases of development and by Agile practices for iterative verification during execution.
SCOPE
IN SCOPE (Defines the features, functional or non-functional requirements of the software that will be tested)
User registration with validations Email functionality with correct SMTP configuration UTM link tracking and signup count update Admin dashboard access and data visualization Spring Boot backend and Oracle DB integration
OUT SCOPE (Defines the features, functional or non-functional requirements of the software that will NOT be tested)
Performance/load testing Cross-browser testing on legacy browsers PDF/Excel report generation (dropped requirement)
QUALITY OBJECTIVE
(Mention the overall objective that you plan to achieve without your testing)
To deliver a stable and reliable ambassador management system with accurate registration, real-time signup tracking, secure backend access, and proper admin control features.
ROLES AND RESPONSIBILITIES
(Detail description of the Roles and responsibilities of different team members)
(Developer & Tester): Responsible for writing, executing test cases, tracking bugs, and verifying fixes. Review test results, verify bug fixes, and ensure quality standards.
TEST METHODOLOGY
OVERVIEW (Mention the reason of adopting a particular test methodology for the project)
The test methodology selected for the project could be • WaterFall
TEST LEVELS (Define the Types of Testing to be executed on the Application Under Test (AUT))
Unit Testing (e.g., updateSignups() method) Integration Testing (Frontend ↔ Backend ↔ DB) System Testing (End-to-End flow validation) Acceptance Testing (Final review before submission)
BUG TRIAGE (Define resolution of each bug, prioritize bugs and determine a schedule for all “To Be Fixed Bugs’)
Critical bugs: Affect functionality like signup failure or email not sent. Fixed immediately. High: Impact reporting
TEST COMPLETENESS (Define the criteria that will deem your testing complete)
All critical and high severity test cases executed End-to-end functionality verifiedlease
TEST DELIVERABLES
(Mention all the Test Artifacts that will be delivered during different phases of the testing lifecycle)
Test Plan Document
RESOURCE AND ENVIRONMENT NEEDS
TESTING TOOLS
Postman (API Testing) Oracle SQL Developer (DB validation)
TEST ENVIRONMENT (Minimum hardware requirements that will be used to test the Application)
Hardware: Windows 11, i5 processor, 8GB Software: STS, Oracle DB, Browser (Chrome), Java 17
ADDITIONAL COMMENTS
Testing was performed manually on local deployment
TEST PLAN
ITEMS TO TEST | TEST DESCRIPTION | TEST START DATE | TEST END DATE | RESPONSIBLE PERSON | STATUS | COMMENTS
Registration Form | Field validations, successful registration | 2025-04-12 | 2025-04-13 | Guguloth Rajkumar | PASSED
Email Sending | SMTP config, fallback, retry | 2025-04-13 | 2025-04-14 | Guguloth Rajkumar | PASSED
UTM Signup Tracking | Correct count update, email match logic | 2025-04-14 | 2025-04-15 | Guguloth Rajkumar | PASSED
Admin Dashboard Access | Role-based access, data view | 2025-04-16 | 2025-04-17 | Guguloth Rajkumar | PASSED
API Testing | POST/GET APIs | 2025-04-17 | 2025-04-18 | Guguloth Rajkumar | PASSED
Final System Testing (UAT) | End-to-end scenario | 2025-04-19 | 2025-04-20 | Guguloth Rajkumar | PASSED
Note on C17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To determine scope, you must – > Precise customer requirement > Project Budget > Product Specification > Skills & talent of your test team
Note on C24: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The objective of the testing is finding as many software defects as possible; ensure that the software under test is bug free before release. To define the test objectives, you should do 2 following steps: > List all the software features (functionality, performance, GUI…) which may need to test. > Define the target or the goal of the test based on above features
Note on C40: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: A Testing Type is a standard test procedure that gives an expected test outcome. all Testing Types are aimed at achieving one common goal “Early detection of all the defects before releasing the product to the customer. There are tons of Testing Types for testing software product. Your team cannot have enough efforts to handle all kind of testing. As Test Manager, you must set priority of the Testing Types > Which Testing Types should be focused for web application testing? > Which Testing Types should be ignored for saving cost? The commonly used testing types are: 1. Unit Testing 2. API Testing 3. Integration Testing 4. System Testing 5. Install/Uninstall Testing 6. Agile Testing You need to decide based on your project scope, time and cost the testing type(s) required for your project
Note on C48: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Test Criteria is a standard or rule on which a test procedure or test judgment can be based. There’re 2 types of test criteria as following Suspension Criteria Specify the critical suspension criteria for a test. If the suspension criteria are met during testing, the active test cycle will be suspended until the criteria are resolved. Exit Criteria It specifies the criteria that denote a successful completion of a test phase. The exit criteria are the targeted results of the test and are necessary before proceeding to the next phase of development. Example: 95% of all critical test cases must pass.