## Instructions
INDUSTRY ACADEMIA COMMUNITY
DOMAIN NAME: | JAVA
INTERN NAME: | GUGULOTH RAJKUMAR
PROJECT NAME: | IAC COMMUNITY AMBASSADOR ONBOARDING PROCESS
DOCUMENT NAME: | Lessons Learnt Log
CREATED ON: | 2025-04-05
Purpose of Document
Lessons Learned Logs are used to capture and share knowledge about what has worked well and what could have been done differently during the planning, management and delivery of an improvement project.
They help others learn from the project team's experience. Lesson Learned Logs: Help support a learning culture.
INSTRUCTIONS:
1. Text in Italics are instructions for completing the document
2. Text in orange is just for reference and should be deleted before submitting the document
3. Comments may be added to some of the cells, please read the comments to better understand the terms
4. All fields must be duly filled
5. The descriptions for what to be filled in each of the fields are provided in the template.
6. Clear all the sample data/instructions provided in the template. The data/instruction provided is only for reference purposes.

## LESSONS LEARNED
LESSONS LEARNED
DOCUMENT VERSION: 1.0
PROJECT NAME | IAC COMMUNITY AMBASSADOR ONBOARDING PROCESS |  |  |  | PLEASE GO THROUGH THE INSTRUCTION SHEET PROVIDED TO GET AN UNDERSTANDING OF HOW TO USE THIS TEMPLATE.
PROJECT ID | IP-6444
PROJECT MANAGER | HARSHADA TOPALE
PROJECT SPONSOR | TUSHAR TOPALE
SL. NO | DATE RAISED | EVENT | LESSON CATEGORY | EARLY WARNING SIGNS? | RECOMMENDATIONS | ACTIONS | OWNER | STATUS | ADDITIONAL COMMENTS
| MENTION THE DATE ON WHICH THE MATTER WAS RAISED | DESCRIBE THE EVENT THAT WAS RAISED | MENTION WHICH CATEGORY THE EVENT WAS RELATED TO | MENTION YES OR NO | MENTION THE RECOMMENDATIONS THAT WAS SUGGESTED FOR SOLVING THE EVENT IF ANY | MENTION THE ACTION SELECTED FOR SOLVING THE VENT | MENTION THE RESPONSIBLE PERSON FOR SOLVING THE EVENT | SOLVED/ PENDING | MENTION IF ANYTHING ELSE OCCURRED DURING THE TIME OF THE MENTIONED EVENT
1 | 2025-03-29 | Late collection of questionnaire data delayed requirement meeting | Requirements Gathering | Yes | Start questionnaire preparation parallelly with charter | Parallel activity planning | Guguloth Rajkumar | SOLVED | Slight rescheduling helped prevent a major delay
2 | 2025-04-05 | RAID log wasn’t fully ready by planning deadline | Planning | Yes | Allocate specific day for risk brainstorming | Created RAID log in focused session | Guguloth Rajkumar | SOLVED | Now RAID log is more complete and usable
3 | 2025-04-01 | SRS took longer than expected due to ambiguity in requirements | Documentation | Yes | Clarify requirements during stakeholder meeting | Improve requirement templates | Guguloth Rajkumar | SOLVED | SRS was delayed by 1 day but planning stage began on time
4 | 2025-04-10 | Frontend and backend integration caused some API issues | Development & Integration | Yes | Predefine common API structures before development | Used Postman to pre-test APIs | Guguloth Rajkumar | SOLVED | Small delay in backend testing was recovered later
5 | 2025-04-18 | Bugs in signup update logic went unnoticed during unit testing | Testing | NO | Include edge cases and null checks in test cases | Wrote additional test cases and retested | Guguloth Rajkumar | SOLVED | JUnit coverage increased and issues were fixed
6 | 23/04/2025 | Project report missed one section initially |  |  | Cross-check with template before final submission | Revisited report template and added missing part | Guguloth Rajkumar | SOLVED | Submitted 1 day before deadline after fix